## Лист1
Booking
Testing areas | Example
Combinatory | search field - filters
Performance | work during holidays, sales periods
Security | types of users, user info, credit cards, text fields etc
Smoke | main functions like registration and log in, search, book, leave a review etc
Integration with 3rd party providers | check and book available slots at hotels, airlines, rental cars etc
Regression
Risk | Nature | Probability | Severity | Mitigation actions
Lack of experience | QA team can have insufficient knowledge, experience with some technologies used in the project | 7 | 9 | Experienced QA team lead can handle this; Estimate more time for investigation
Change of requirements | Requirements can be changed according to market | 5 | 6 | Communication with stakeholders clarifies all changes (new requirements, time, cost)
Leaving of a team member | Some of the QA team can deside to leave the project | 2 | 5 | Every team member has good undrestanding of all parts of the project. Low-level documentation
Closing a part of the project | If the customer decides to close a part of the project | 1 | 6 | Low-level documentation. Linked documentation. Independent parts of the project. New job opportunities for stuff
An automated test ran once | Wrong selection of tests for automation | 3 | 1 | Automated testing is rather expensive so it is necessary to select tests for automation consciously
Tools | Licence | Browser | Area | For Junior |  | Reports | Languages | Additional
Katalon | free | cross-browser | APIs, Web and mobile (Android and iOS) | straightforward mode, Record and play tester's steps is available; for experienced - coding mode |  | analysis reports and test recording | Groovy | Supports parallel and sequential executions and can perform remote and local testing
Selenium | free | cross-browser | Web | Selenium IDE - record and play tester's steps is available |  | available with frameworks (eg. Allure) | Python, Java, C#, Scala, Groovy, Ruby, Perl, and PHP. | Concists several componentsto provide a complete web application test automation. Often used for regression testing
Zed Attack Proxy | free | cross-browser | Web | intuitive GUI |  | available | - | Missing anti-CSRF tokens and security headers; Session ID in URL rewrite; SQL injection; XSS injection
Estimate
Area | Component | Element | Best case, | Most likely, | Worst likely,
|  |  | story points | story points | story points
Main page | Landing | tabs | 1 | 1 | 2
|  | currency | 1 | 1 | 2
|  | languages | 2 | 2 | 3
|  | Help center | 3 | 3 | 5
|  | Messages | 2 | 3 | 5
|  | Notifications | 1 | 1 | 2
|  | Register | 1 | 2 | 3
|  | Sign in | 1 | 2 | 3
| Search field |  | 2 | 3 | 5
| Banners |  | 2 | 3 | 5
| Subscribe fileds |  | 2 | 3 | 5
| Footer | links with pages on them | 5 | 8 | 13
User account | Manage account | Personal detailes | 2 | 3 | 5
|  | Preferences | 1 | 2 | 2
|  | Security | 2 | 3 | 5
|  | Payment details | 1 | 2 | 3
|  | Email notifications | 2 | 3 | 5
|  | Other traveler | 1 | 2 | 3
| Bookings | search bookings | 2 | 3 | 5
|  | Booking detailes | 2 | 3 | 5
| Genius program |  | 5 | 8 | 13
| Saved |  | 2 | 3 | 5
| Sign out |  | 1 | 1 | 2
Hotels.Advanced search | Search field |  | 2 | 2 | 3
| Map |  | 2 | 3 | 5
| Filters |  | 5 | 5 | 8
| Sorting |  | 2 | 3 | 5
| Search results | Property field | 2 | 3 | 5
Hotels.Hotel page | Top field |  | 3 | 5 | 8
| Info fields |  | 3 | 5 | 8
| Availability |  | 3 | 5 | 8
| Guest reviews |  | 2 | 3 | 5
| Got a question? |  | 1 | 2 | 3
Hotels.Reservation | Booking detailes |  | 2 | 3 | 5
| User detailes |  | 3 | 3 | 5
| Payment | online | 3 | 5 | 8
|  | on site | 1 | 2 | 2
| Confirmation |  | 2 | 3 | 5
| Contact hotel |  | 1 | 2 | 3
| Contact booking.com |  | 1 | 2 | 3
| Edit reservation |  | 1 | 2 | 3
| Cancel reservation |  | 2 | 3 | 5
Flights.Flights page | Search field |  | 2 | 3 | 5
| Banners |  | 2 | 3 | 5
Flights.Search page | Filters |  | 2 | 3 | 5
| Search results |  | 2 | 3 | 5
Flights.booking page | Ticket type |  | 2 | 3 | 5
| User info |  | 2 | 3 | 5
| Payment |  | 3 | 5 | 8
Cars.rental page | Search field |  | 2 | 3 | 5
| Banners |  | 2 | 3 | 5
| Info fields |  | 1 | 2 | 3
Cars.booking page | Map |  | 2 | 3 | 5
| Search results |  | 2 | 3 | 5
Cars.Partner booking page | Filters |  | 3 | 5 | 8
| Car selector |  | 1 | 2 | 3
| Car info fields |  | 2 | 3 | 5
| Book with protection |  | 2 | 3 | 5
| Book without protection |  | 2 | 3 | 5
Cars.Options | Booking detailes |  | 2 | 3 | 5
| Car detailes |  | 3 | 5 | 8
| Review score breakdown |  | 2 | 3 | 5
| Important info |  | 1 | 2 | 3
Cars. Driver info |  |  | 2 | 3 | 5
Cars.Payment |  |  | 3 | 5 | 8
Cars.Confirmation |  |  | 2 | 2 | 3
Cars.Cancelation |  |  | 2 | 3 | 5
Taxi.Booking page | Search field |  | 2 | 3 | 5
| Banners |  | 1 | 2 | 3
| Header |  | 1 | 2 | 3
| Footer with links |  | 3 | 5 | 8
Taxi.Reservarion | Booking detailes |  | 2 | 3 | 5
| Choose taxi |  | 1 | 2 | 3
| Info fields |  | 2 | 3 | 5
| Payment |  | 3 | 5 | 8
| Edit reservation |  | 1 | 2 | 3
Attractions.Booking page | Search field |  | 1 | 2 | 3
| Top destanations |  | 1 | 2 | 3
| More destanations | Cities | 13 | 21 | 34
Attractions.Search results | Filters |  | 2 | 3 | 5
| Sorting |  | 1 | 1 | 2
Attractions.Reservation | Info fields |  | 1 | 2 | 3
| Tickets and prices |  | 1 | 2 | 3
| Reservation |  | 2 | 3 | 5
Attractions.Payment |  |  | 3 | 5 | 8
Rent out an appartment | Landing |  | 1 | 1 | 2
| Info blocks | Links | 3 | 5 | 8
Partner.Registration | email page |  | 1 | 2 | 3
| contact detailes page |  | 1 | 2 | 3
| password page |  | 1 | 2 | 3
| Confirmation |  | 1 | 2 | 3
List your property start page |  |  | 1 | 2 | 3
List appartment |  |  | 5 | 8 | 13
List home |  |  | 5 | 8 | 13
List Hotel |  |  | 5 | 8 | 13
List alternetive place |  |  | 5 | 8 | 13
Careers | Home |  | 2 | 3 | 5
| Locations |  | 2 | 3 | 5
| Teams | jobs | 3 | 5 | 8
| About us | Our story | 2 | 3 | 5
|  | our people | 1 | 2 | 3
|  | inclusion | 2 | 3 | 5
|  | our horizons | 2 | 3 | 5
|  | sustainability | 3 | 5 | 8
| How we are |  | 2 | 3 | 5
| Landing |  | 2 | 3 | 5
Employee access |  |  | 13 | 21 | 34
|  | Sum= | 240 | 375 | 606
|  | Estimate= | 391
|  | Standart deviation= | 61